## Sheet1
Git |  |  | Hours Spent
Commit | Branch | Date
First Git Version | Master | 2015-04-04 | 22
Added Post Pickers | Master | 2015-04-04 | 4
Posts can be submitted | Master | 2015-04-04 | 3
Final Storyboard Layout | Master | 2015-04-05 | 4
Moderator Functionality and Scan Filters | Master | 2015-04-06 | 3
BLE functionality | Master | 2015-04-09 | 5
Board List Functionality | Master | 2015-04-11 | 3
Board list and table update | Master | 2015-04-12 | 2
Storyboard tuning | Master | 2015-04-14 | 2
Revamp Storyboard Added Search | Master | 2015-04-14 | 6
Search Screen Selection and Segues | Master | 2015-04-19 | 5
BLE Scan Fix | Master | 2015-04-21 | 1
Massive Refactoring | Master | 2015-04-23 | 6
Board class update | Master | 2015-04-23 | 1
Post Saving | Master | 2015-04-26 | 8
Board Saving | Master | 2015-04-26 | 4
Moderator Login and Post Filtering | Master | 2015-04-30 | 4
Email Notifications | Master | 2015-05-02 | 3
Background Beacon Scanning | Master | 2015-05-05 | 5
Notifications and Indicators | Master | 2015-05-24 | 5
Ban List, Alert Boxes, Validation, and Navigation | Master | 2015-05-29 | 7
Redesign Post Viewing | Master | 2015-05-30 | 3
Getsure Recognizers | Master | 2015-05-31 | 2
Outdated Post Removal and UI Tuning | Master | 2015-05-31 | 3
Tab Bar Icons | Master | 2015-06-01 | 1
More Gestures | Master | 2015-06-05 | 3
HTML Viewing | Master | 2015-06-08 | 2
Refactoring and Commenting | Master | 2015-06-23 | 3
View Controller Comments | Master | 2015-06-28 | 3
Finish Comments | Master | 2015-06-29 | 2
Total |  |  | 125